## Tasks
ID | Name | Description | Status | Assigned to | Depends on | Total Tasks | Open Tasks | Not Started | In Progress | Blocked | Testing | Completed
1 | Create login/logout functionality (backend) | Create the ability to take in the credentials passed from the frontend and use it to validate and login the user. | Complete | Remi |  | 31 | 2 | 2 | 0 | 0 | 0 | 29
2 | Create login functionality (frontend) | Create ability to receive login session from the backend and manage it on the frontend | Complete | Trevor/Brandon
3 | Refine recommendation procedure | Refine the function so that it does not display the input title as a recoemmendation. Also remove any items in the users watchlist from the recommendations also. | Complete | Brandon
4 | Populate the title page | Send title ID to backend, get title information | Complete | Trevor
4.1 | Recommendation - Front end | Pull to get recommendations for the title using the algorithim | Complete | Trevor/Brandon | 4.2
4.2 | Recommendation - Back end | Get route working for recs | Complete | Remi/Brandon
4.3 | Display reviews to the title page |  | Complete | Trevor/Brandon
5 | Add search functionality | Ability to search part of a title name, and return list of titles the user can select from | Complete | Trevor
6 | Remove DB password from source code | Currently, the app.py file has the DB password as clear text being exposed. This needs to be remediated. | Complete | Remi
7 | Watchlist page - front end | Get all functionality working for the watchlist | Complete | Trevor/Brandon
8 | Review Page - backend | Route to write user reviews to DB | Complete | Remi
9 | Review Page - Frontend | Form to write reviews and POST to the backend | Complete | Trevor/Brandon
10 | User Watchlist Route - backend | Fix userwatchlist DELETE route | Complete | Remi
11 | Limit: search titles, title: 3-4 actors |  | Complete | Remi
12 | return genre for any time we need a title |  | Complete | Remi
13 | in add/delete watchlist make so it cannot duplicate titles |  | Complete | Remi
15 | Add review_title column to user_review table |  | Complete | Remi/Brandon
14 | return genre name for additional pages | search, watchlist, home watchlist | Complete | Remi
16 | fix multiple frontend calls to the same backend route issue |  | Complete | Trevor
17 | add dummy review data for titles |  | Complete | Brandon
18 | Random title page | backend return random title ID that exists to frontend | Complete | Remi/Trevor
19 | Create function for getting average review and return it as part of the /title/title_id endpoint. |  | Complete | Remi/Brandon
20 | Return top_rating data for home page. |  | Complete | Remi
23 | Forgot password page | We never implemented this yet, frontend would send email with new password | Complete | All
23 | Add user rating to recommedation alg |  | Complete | Brandon
24 | Add director name to title page |  | Complete | Remi/Trevor
25 | Implement token_refresh on backend |  | Complete | Remi
26 | Remove titles in DB without acotrs/directors | if there is too many of them then we can skip this | Not Started | Brandon
27 | Remove actors/directors with no last names | Some names just show up as like "Dan" which isnt helpful and doesnt look great | Not Started | Brandon
28 | check if refresh token is valid or not |  | Complete | Remi
29 | Data validation improvement on account creation | Add some additional data validation checks | Complete | Trevor/Brandon

## Values
Status
Not Started
In Progress
Blocked
Testing
Complete